## Drawing Reviw（R240)
SN | Build | Status | Risk level | SMP Vendor | APN(rev) | Category | Part Description | Callout | Proposal | Issue date | Close date | IR DRI | CUPO DRI | PD | PD disposition | new drawing | new drawing description | Link
1 | DVT | Open | Mid | MGS | 099-53721-09 (160-06671) | Spec proposal | MAG,BACK,RAIL,02,R240 | Base on colleting data, the MM value data is low CPK(0.705) under this Spec(5.68~6.68 µWb*cm). | Propose MM Spec is 6.386±0.51 µWb*cm, CPK =1.579, Can meet CPK 1.33 requirement. | 2025-12-22 |  | Ellen |  | Justin Roffman |  |  |  | 099-53721-09
2 | DVT | Open | Mid | MGS | 099-53721-09 (160-06672) | Spec proposal | MAG,BACK,RAIL,01,R240 | For our last lot magnet, the MM value data is low CPK(1.055) under this Spec(3.18~3.74 µWb*cm). | Propose MM Spec is 3.510±0.28 µWb*cm, CPK=1.448,Can meet CPK 1.33 requirement. | 2025-12-22 |  | Ellen |  | Justin Roffman |  |  |  | 099-53721-09

## CDML
SN | Build | Status | Risk level | SMP Vendor | APN(rev) | Category | Part Description | Issue description | Proposal | Issue date | Close date | IR DRI | CUPO DRI | PD | PD disposition | Link

## YGA Tracker（R240）
SN | Build | Status | Risk level | Next Step | SMP Vendor | APN(rev) | Part Description | SPC No | Dim Description | Base on drawing |  |  |  |  | Base on spec proposal |  |  |  |  | Failure Analysis | Corrective Action | Close date | IR DRI | CUPO DRI | PD | PD disposition | Link
[10 empty] | Nominal | Tol+ | Tol- | Yield | CPK | Nominal | Tol+ | Tol- | Yield | CPK
1 | DVT | Closed | High | Drawing update due to incorrect callout | MGS | 099-53721-08 (160-06671) | MAG,BACK,RAIL,02,R240 | SPC D | MM | 5.47 | 0.44 | -0.44 | 0% | -1.405 | Collect data |  |  |  |  | In DVT build, 2x magnets 160-06671 and 160-06672 are new added magnet.These have the same grade, width, and thickness as the MP build magnet 160-05550, differing only in length. Based on the simulated volume changes, the theoretical range of the MM value is shown in the table below. The actual MM value exceeds the 2D drawing Spec, but falls on the theoretical MM range. DVT阶段新增2颗磁钢与量产磁钢160-05550性能、宽度以及厚度相同，仅长度有差异。根据模拟体积变化计算,MM 值的理论范围如下表: 实际测试值超过 2D 图纸规格，但是在理论计算范围内。 | Continue to collect MM data. 建议继续收集MM数据 | 2025-12-21 | Ellen |  | Justin Roffman | MM to update in next revision based on data collected | 099-53721-08
2 | DVT | Closed | High | Drawing update due to incorrect callout | MGS | 099-53721-08 (160-06672) | MAG,BACK,RAIL,01,R240 | SPC D | MM | 3.19 | 0.24 | -0.233 | 0% | -2.408 | Collect data | [6 empty] | 2025-12-21 | Ellen |  | Justin Roffman |  | 099-53721-08

## Category
DR category | Risk | YGA next step | Risk
Design change proposal, | High Risk | Drawing update due to process capability limitation | Mid
Process limitation, | Mid Risk | Process Improvement | Low
Measure limitation, | High Risk | Drawing update due to measurement capability limitation | Mid
SPC over control, | Low risk | Drawing update due to incorrect callout | High
Spec proposal, | Mid Risk
Close loop dim, | Mid Risk
Mixing risk, | High Risk
APN missed, | High Risk
Incorrect callout, | High Risk
Excess dimension or APN, | Low risk
Dim missed,2D&3D mismatch, | High Risk
Legacy best practice, | Low risk
Rev mismatch | Low risk
High risk | Block production or shipment
Low risk | Not block production or shipment

## Small part status tracker (hidden)
Picture | Build | Part Name | material brand | Part Number | Drawing Release | Drawing Review | MTD | Gauge list | OQC | ORT Fixture | Q-Plan | FAI/CPK | Cosmetic yield study | Yield Gap | Supplier | 1st Shipping Deadline
| P1 | MAG,HES,PALM_REST,P0,R428 | N45SH-100RC | 160-04299-06 | 2023-01-04 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-02-22 | / | / | QDT | 2023-02-27
| P1 | MAG,HES,PALM REST,R418 | N45SH-100RC | 160-04390-01 | 2023-01-30 | / | 2023-02-07 |  |  |  | 2023-02-07 | TBD | / | / | QDT | TBD
| P1 | MAG,MONO,LATCH, ARROW SIDE,R418 | N45SH-100RC | 160-04349-08 | 2023-02-02 | / | 2023-02-10 | / | / | / | 2023-02-10 | 2023-02-22 | / | / | QDT | 2023-02-27
| P1 | MAG,MONO,LATCH, ESCAPE SIDE,R418 | N45SH-100RC | 160-04350-08 | 2023-02-02 | / | 2023-02-10 | / | / | / | 2023-02-10 | 2023-02-22 | / | / | QDT | 2023-02-27
| P1 | MAG,HES,PALM_REST,LP,P1,R418 | N45SH-100RC | 160-04383-03 | 2023-01-30 | / | 2023-02-07 | / | / | / | 2023-02-07 | TBD | / | / | QDT | TBD
| P1 | ASSY,MAGARRAY,C1, P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44477-04 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,3.7X3.5X1.23, P1,R418 | N45SH-100RC | 160-04366-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,S4.1X1.23,P1, R418 | N45SH-100RC | 160-04367-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,S3.5X1.23,P1, R418 | N45SH-100RC | 160-04368-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C1,P1,R418 | SPCD 1010 | 806-41982-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY, C2A,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44478-03 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,3.7X3.5X1.23, P1,R418 | N45SH-100RC | 160-04366-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,4.5X3.7X1.23, P1,R418 | N45SH-100RC | 160-04369-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,3.5X2.7X1.23, P1,R418 | N45SH-100RC | 160-04370-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C2A,P1, R418 | SPCD 1010 | 806-41983-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY, C2B,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44479-03 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,4.5X3.7X1.23, P1,R418 | N45SH-100RC | 160-04369-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,3.5X2.7X1.23, P1,R418 | N45SH-100RC | 160-04370-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C2B,P1, R418 | SPCD 1010 | 806-41986-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY, C2C,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44480-05 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,3.2X2.6X1.23, P1,R418 | N45SH-100RC | 160-04371-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C2C,P1, R418 | SPCD 1010 | 806-41987-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY,C3, P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44481-05 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,S3.5X1.23,P1, R418 | N45SH-100RC | 160-04368-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,4.5X3.7X1.23, P1,R418 | N45SH-100RC | 160-04369-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG, 6.39X3.6X1.23,P1, R418 | N45SH-100RC | 160-04373-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C3,P1,R418 | SPCD 1010 | 806-41988-05 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY, C3A,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44711-03 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,S3.5X1.23,P1, R418 | N45SH-100RC | 160-04368-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,5.4X3.5X1.23, P1,R418 | N45SH-100RC | 160-04372-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C3A,P1, R418 | SPCD 1010 | 806-42147-04 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY,C4, P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44482-03 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,S4.1X1.23,P1, R418 | N45SH-100RC | 160-04367-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,S3.5X1.23,P1, R418 | N45SH-100RC | 160-04368-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,3.5X2.7X1.23, P1,R418 | N45SH-100RC | 160-04370-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,5.4X3.5X1.23, P1,R418 | N45SH-100RC | 160-04372-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,4.1X2.7X1.23, P1,R418 | N45SH-100RC | 160-04374-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,C4,P1,R418 | SPCD 1010 | 806-41989-05 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAGARRAY,O2, P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44483-05 | 2023-01-09 | / | 2023-01-16 | / | / | / | 2023-01-16 | 2023-03-04 | / | / | QDT | 2023-03-09
| P1 | MAG,3.5X2.7X1.23, P1,R418 | N45SH-100RC | 160-04370-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | MAG,4.1X2.7X1.23, P1,R418 | N45SH-100RC | 160-04374-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | SHUNT,O2,P1,R418 | SPCD 1010 | 806-41990-03 | 2023-01-03 | / |  | / | / | / |  | 2023-03-04 | / | / | QDT
| P1 | ASSY,MAG_ARRAY, LP,L1,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44749-06 | 2023-02-02 | 2023-02-03 | 2023-02-10 | / | / | / | 2023-02-10 | TBD | / | / | QDT | TBD
| P1 | MAG,LP,L1,P1, R418 | N45SH-100RC | 160-04381-06 | 2023-02-02 | 2023-02-03 |  | / | / | / |  | TBD | / | / | QDT
| P1 | SHUNT,LP,L1,P1, R418 | SPCD 1010 | 806-42227-05 | 2023-02-02 | 2023-02-03 |  | / | / | / |  | TBD | / | / | QDT
| P1 | ASSY.MAG_ARRAY, LP,L3,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44750-05 | 2023-02-02 | 2023-02-03 | 2023-02-10 | / | / | / | 2023-02-10 | TBD | / | / | QDT | TBD
| P1 | MAG,LP,L2,P1, R418 | N45SH-100RC | 160-04382-06 | 2023-02-02 | 2023-02-03 |  | / | / | / |  | TBD | / | / | QDT
| P1 | SHUNT,LP,L3,P1, R418 | SPCD 1010 | 806-42228-05 | 2023-02-02 | 2023-02-03 |  | / | / | / |  | TBD | / | / | QDT
| P1 | ASSY,MAG_ARRAY, LP,L2,P1,R418 | N45SH-100RC+ SPCD 1010 | 604-44751-05 | 2023-02-02 | 2023-02-03 | 2023-02-10 | / | / | / | 2023-02-10 | TBD | / | / | QDT | TBD
| P1 | MAG,LP,L2,P1, R418 | N45SH-100RC | 160-04382-06 | 2023-02-02 | 2023-02-03 |  | / | / | / |  | TBD | / | / | QDT
| P1 | SHUNT,LP,L2,P1, R418 | SPCD 1010 | 806-42229-05 | 2023-02-02 | 2023-02-03 |  | / | / | / |  | TBD | / | / | QDT
| Open | Put a expected submission date | [8 empty] | For CPK: | Submit + Approved /Shipped
| Ongoing | Put a planned date | [9 empty] | Submit + No Approval Yet
| Done | Put finished date inside | [9 empty] | Unsubmit
Not Applicable