## Introduction
MIL format A - Common Part
No | Issue Description | APN | Pic | Yield Loss By Build |  |  | Root Cause | Corrective Action | DRI | Due Date | Status
|  |  |  | P1 | P2 | EVT
APN1
APN2
APN3
MIL format B - NUD part
No | APN | Issue Description | Pic | Yield Loss By Build |  |  | Root Cause | Corrective Action | DRI | Due Date | Status
|  |  |  | P1 | P2 | EVT
APN1
APN2
Remark:
1 | 对于NUD（New,Unique,Difficult) parts，需要全部的不良List Down并且进行失效分析（含单件，比如B735斜取向磁铁，B482 角度全检磁铁）
2 | 对于Pencil magnet,每个组件都需要有单独的MIL
3 | Piece Part,可以把全部料号合并写一个整体MIL
4 | 对于需要全检的项目，所有良率损失都需要有记录
5 | Rigid bonded magnet 等其它一些NUD磁铁，请单独添加Yield Summary 和 MIL

## Summary
| Product type | APN | Shipping to | Vendor | Yield target | P1 | EVT | DVT | wk03 | wk04 | wk05 | wk06 | wk07 | wk08 | wk09 | wk10 | wk11 | wk12 | wk13 | wk14 | wk15 | wk16 | wk17 | wk18 | wk19 | wk20 | wk21
1 | Pencil Magnet-Assy | 604-59890 | Jabil | MGS | 97.49% | / | 97.49% | /
2 | Pencil Magnet-Assy | 604-59891 | Jabil | MGS | 97.36% | / | 97.36% | /
3 | PP magnet | 160-05846(1) | ADV/Tarry | MGS | 98.71% | / | 98.71% | 2025-12-31
4 | PP magnet | 160-05847(2) | ADV/Tarry | MGS | 99.05% | / | 99.05%
5 | PP magnet | 160-05849(3) | ADV/Tarry | MGS | 98.43% | / | 98.43%
6 | PP magnet | 160-05851(4) | ADV/Tarry | MGS | 98.21% | / | 98.21%
7 | PP magnet | 160-05844(5) | ADV/Tarry | MGS | 98.13% | / | 98.13%
8 | PP magnet | 160-05852(6) | ADV/Tarry | MGS | 98.36% | / | 98.36%
9 | PP magnet | 160-05850(7) | ADV/Tarry | MGS | 99.16% | / | 99.16%
10 | PP magnet | 160-05848(8) | ADV/Tarry | MGS | 98.61% | / | 98.61%
11 | PP magnet | 160-05845(9) | ADV/Tarry | MGS | 99.14% | / | 99.14%
12 | PP magnet | 160-05549(10) | ADV/Tarry | MGS | 98.11% | 97.34% | 98.89%
13 | PP magnet | 160-05550(11) | ADV/Tarry | MGS | 98.13% | 97.55% | 98.72%
14 | PP magnet | 160-05551(12) | ADV/Tarry | MGS | 98.1% | 97.64% | 98.56%
15 | PP magnet | 160-05552(13) | ADV/Tarry | MGS | 98% | 97.25% | 98.75%
16 | PP magnet | 160-05553(14) | ADV/Tarry | MGS | 98% | 97.15% | 98.86%
17 | PP magnet | 160-05554(15) | ADV/Tarry | MGS | 98.52% | 98.07% | 98.98%
18 | PP magnet | 160-05555(16) | ADV/Tarry | MGS | 98.51% | 98.3% | 98.71%
19 | PP magnet | 160-05556(17) | ADV/Tarry | MGS | 98.04% | 97.45% | 98.62%
20 | PP magnet | 160-05842(18) | ADV/Tarry | MGS | 98.7% | / | 98.7%
21 | PP magnet | 160-05843(19) | ADV/Tarry | MGS | 97.85% | / | 97.85%
22 | PP magnet | 160-05861(20) | ADV/Tarry | MGS | 99.17% | / | 99.17%
23 | PP magnet | 160-05857(21) | ADV/Tarry | MGS | 98.94% | / | 98.94%
24 | PP magnet | 160-05858(22) | ADV/Tarry | MGS | 98.46% | / | 98.46%
25 | PP magnet | 160-05859(23) | ADV/Tarry | MGS | 98.43% | / | 98.43%
26 | PP magnet | 160-05860(24) | ADV/Tarry | MGS | 98.59% | / | 98.59%
27 | PP magnet | 160-05855(25) | ADV/Tarry | MGS | 98.94% | / | 98.94%
28 | PP magnet | 160-05856(26) | ADV/Tarry | MGS | 98.55% | / | 98.55%
29 | PP magnet | 160-05853(27) | ADV/Tarry | MGS | 99% | / | 99%
30 | PP magnet | 160-05854(28) | ADV/Tarry | MGS | 99.16% | / | 99.16%
31 | PP magnet | 160-05841(29) | ADV/Tarry | MGS | 97.68% | / | 97.68%
32 | PP magnet | 160-05570(30) | ADV/Tarry | MGS | 98.98% | 99.07% | 98.88%
33 | PP magnet | 160-05571(31) | ADV/Tarry | MGS | 98.41% | 97.87% | 98.95%
34 | PP magnet | 160-05748(32) | ADV/Tarry | MGS | 98.22% | 97.97% | 98.46%
35 | PP magnet | 160-05744(33) | ADV/Tarry | MGS | 98.15% | 97.44% | 98.87%
36 | PP magnet | 160-06041(34) | ADV/Tarry | MGS | 97.86% | / | 97.86%
37 | PP magnet | 160-05578(35) | ADV/Tarry | MGS | 98.72% | / | 98.72%
38 | PP magnet | 160-05579(36) | ADV/Tarry | MGS | 98.59% | / | 98.59%
39 | PP magnet | 160-05580(37) | ADV/Tarry | MGS | 99.38% | / | 99.38%
40 | PP magnet | 160-05583(38) | ADV/Tarry | MGS | 98.57% | / | 98.57%
41 | PP magnet | 160-05584(39) | ADV/Tarry | MGS | 99.62% | / | 99.62%
42 | PP magnet | 160-05585(40) | ADV/Tarry | MGS | 98.92% | / | 98.92%
43 | PP magnet | 160-05586(41) | ADV/Tarry | MGS | 98.35% | / | 98.35%
44 | PP magnet | 160-05587(42) | ADV/Tarry | MGS | 98.71% | / | 98.71%
45 | PP magnet | 160-05589(43) | ADV/Tarry | MGS | 99.01% | / | 99.01%
46 | PP magnet | 160-05590(44) | ADV/Tarry | MGS | 98.37% | / | 98.37%
47 | PP magnet | 160-05750(45) | ADV/Tarry | MGS | 98.42% | / | 98.42%
48 | PP magnet | 160-05592(46) | ADV/Tarry | MGS | 98.79% | / | 98.79%
49 | PP magnet | 160-05593(47) | ADV/Tarry | MGS | 98.91% | / | 98.91%
50 | PP magnet | 160-05752(48) | ADV/Tarry | MGS | 99.02% | / | 99.02%
51 | PP magnet | 160-05557(49) | ADV/Tarry | MGS | 98.71% | / | 98.71%
52 | PP magnet | 160-05755(50) | ADV/Tarry | MGS | 98.12% | / | 98.12%
53 | PP magnet | 160-05756(51) | ADV/Tarry | MGS | 98.33% | / | 98.33%

## Sheet2 (2) (hidden)
build | yield
May | 90.88%
June | 91.2%
July | 0%
August | 0%
May | 0%
June | 64.15%
July | 88.97%
August | 91.11%
May | 93.51%
June | 92.7%
July | 91.8%
August | 94.46%
May | 91.03%
June | 0%
July | 0%
August | 94.07%
May | 91.76%
June | 92.85%
July | 94.35%
August | 95.49%
May | 85.63%
June | 86.14%
July | 0%
August | 0%
May | 92.77%
June | 93.97%
July | 93.13%
August | 0%
May | Producing
June | 94.44%
July | 0%
August | 0%
May | 93.15%
June | 0%
July | 0%
August | 0%
May | 92.7%
June | 0%
July | 0%
August | 95.26%
May | 0%
June | 95.71%
July | 96.13%
August | 96.42%

## FAM Ring (manual Line) (hidden)
No. | A P/N | Pic | Issue | Root cause | Improvement action | DRI | Date | ww | EVT | WK23 | WK24 | WK25 | WK26 | [9 empty] | wk38 | wk39
[8 empty] | APN | 604-39297-06 | 604-39297-06 | 604-39297-06 | 604-39297-06 | 604-39297-06
[8 empty] | Yield | 90.88% | no input | 91.07% | no input | 91.35% | no input | no input | no input | no input | #DIV/0! | #DIV/0! | no input | no input | no input | no input | no input
[8 empty] | Total Output | 2523 |  | 1939 |  | 2629
1 | 604-39297-06 |  | Mesh offset | OP take the mesh into the fixture by manual. Becuse OP was not skilled, it was cause that the mesh was offset in the fixture. | 1. Train OP and the exercise time is more than 4H to improve OP's skill, than OP can work. 2.After OP take the mesh into the fixture, OP must inspect whether the mesh is offset in the fixture,then assemble plastic part. | Caotianyuzhaiyanhong | 2022-07-05 | Defect Qty | 101 |  | 36 |  | 75
[8 empty] | % | 4.003% | #DIV/0! | 1.857% | #DIV/0! | 2.853% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
2 |  |  | Bottom PSA offset | OP take the mesh into the fixture by manual. Becuse OP was not skilled, it was cause that the mesh was offset in the fixture. | 1. Train OP and the exercise time is more than 4H to improve OP's skill, than OP can work. 2.After OP take the mesh into the fixture, OP must inspect whether the mesh is offset in the fixture,then assemble plastic part. | Caotianyuzhaiyanhong | 2022-07-05 | Defect Qty | 69 |  | 106 |  | 79
|  |  |  | OP take the mesh into the fixture by manual. Becuse OP was not skilled, it was cause that the mesh was offset in the fixture. | 1. Train OP and the exercise time is more than 4H to improve OP's skill, than OP can work. 2.After OP take the mesh into the fixture, OP must inspect whether the mesh is offset in the fixture,then assemble plastic part. | Caotianyuzhaiyanhong |  | % | 2.735% | #DIV/0! | 5.467% | #DIV/0! | 3.005% | #DIV/0! | #DIV/0! | #DIV/0!
3 |  |  | TOP PSA offset | OP take the mesh into the fixture by manual. Becuse OP was not skilled, it was cause that the mesh was offset in the fixture. | 1. Train OP and the exercise time is more than 4H to improve OP's skill, than OP can work. 2.After OP take the mesh into the fixture, OP must inspect whether the mesh is offset in the fixture,then assemble plastic part. | Caotianyuzhaiyanhong | 2022-07-05 | Defect Qty | 61 |  | 84 |  | 96
[5 empty] | 1. Train OP and the exercise time is more than 4H to improve OP's skill, than OP can work. 2.After OP take the mesh into the fixture, OP must inspect whether the mesh is offset in the fixture,then assemble plastic part. | Caotianyuzhaiyanhong |  | % | 2.418% | #DIV/0! | 4.332% | #DIV/0! | 3.652% | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | % | 0% | #DIV/0! | 0% | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | % | 0% | #DIV/0! | 0% | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[8 empty] | % | 0% | #DIV/0! | 0% | #DIV/0! | 0% | #DIV/0! | #DIV/0! | #DIV/0!
[13 empty] | 2629 | 939 | 1690 | 0.64283
330

## Pencil Magnet
APN | Issue | P1 |  |  | EVT |  |  | MP
|  | Qty Loss | Total Qty | Yield | Qty Loss | Total Qty | Yield | Qty Loss | Total Qty | Yield
604-56970-06 | Scratch | 40 | 2158 | 1.854% | / | / | /
| Magnet misalignment | 15 | 2158 | 0.6951% | / | / | /
| chips | 3 | 2158 | 0.139% | / | / | /
604-58209-01 | Magnet misalignment | 26 | 2560 | 1.016% | / | / | /
| Pet Mismatch | 18 | 2560 | 0.7031% | / | / | /
| chips | 3 | 2550 | 0.1176% | / | / | /
604-59890 | Scratch | / | / | / | 47 | 4168 | 1.128%
| Magnet misalignment | / | / | / | 34 | 4168 | 0.8157%
| Foreign | / | / | / | 22 | 4168 | 0.5278%
604-59891 | Scratch | / | / | / | 48 | 3841 | 1.25%
| Magnet misalignment | / | / | / | 31 | 3841 | 0.8071%
| Foreign | / | / | / | 23 | 3841 | 0.5988%

## Pencil Magnet MIL
Magnet Type: Pencil Magnet
No | APN | Issue Description | Pic | Yield Loss By Build |  |  | Root Cause | Corrective Action | DRI | Due Date | Status
|  |  |  | P1-1 | EVT | MP
1 | 604-56970-06 | Scratch |  | 1.854% |  |  | 磁铁镀层为蓝白锌，摩擦过程中会发黑；且镀层较软，组装过程中会产生划痕。 | PD 发行V09图纸，将镀层改为镍铜镍，电镀厂提供镍铜镍的产品给磁声组装验证。 | PD | 2025-03-10 | Closed
2 |  | Magnet misalignment |  | 0.6951% |  |  | When the 326 glue level is too low，there is a chance that magnet will detach from the glue surface. 326 胶水偏下限时会有比例磁铁脱胶 | Change the PSA design and increase the area of the 326 adhesive layer. 变更PSA的设计， 增大326胶水的粘接面积。 | PD | 2025-03-12 | Closed
3 | 604-58209-01 | Magnet misalignment |  | 1.016% |  |  | 1. 326 胶水不均匀，导致磁钢因粘结效果不好，磁钢错位 2. 磁钢之间极性排斥，导致磁钢凸起 | 1. 优化胶路，避免胶量波动。直线改为打点 2. 优化涂覆活化剂方式 | 陈俊宏 桑涛 | Next Build | Cancel
4 |  | Pet Mismatch 黄膜偏移 |  | 0.7031% |  |  | PET上有个别孔位位置偏移，导致膜偏 | 供应商修模，已经修模完成。 | 供应商 | Next Build | Cancel
5 | 604-59890 | Scratch | #VALUE! |  | 1.18% |  | The production assembly line consists of three processes: first assembly, magnetizing, and second assembly. The abnormality occurred during the magnetizing process, where burrs on the magnetizing board's acupuncture points caused scratches when removing the semi-finished products after magnetization. 此次生产组装线是有三道工序，一道组装——充磁——二道组装，异常发生在充磁工序，充磁治具板穴位有毛刺导致磁钢在充完磁后取下时被划伤。 | Repaired and remagnetized fixture, no scratches after deburring and milling. 返修充磁治具，铣去毛刺后无划伤产生。 | 桑涛 喻光锋 | 2025-06-18 | Closed
6 |  | Magnet misalignment | #VALUE! |  | 0.84% |  | "This anomaly occurred after magnetization, due to the influence of the Halbach array, the repulsive force between magnets increased. Additionally, the curing time of the 326 adhesive was too long, resulting in magnet detachment. 此异常出现在充磁之后，受海尔贝克阵列影响，磁钢之间排斥力增大，外加326胶水的固化时间过长，导致磁钢脱落" | "Technical personnel are continuously analyzing. 技术持续分析中。" | 桑涛 陈俊宏 喻光锋 | TBD | Cancel
7 |  | Foreign | #VALUE! |  | 0.53% |  | "The design of the blueprint resulted in areas where adhesive was exposed, which attracted dust from the air and caused foreign particles to appear. 图纸设计导致出现露出胶的位置，该位置吸附空气中的灰尘导致出现异物" | "PD Update: Version 03 Drawing - Eliminate Adhesive Exposure Position PD更新03版图纸取消露胶位置" | 桑涛 陈俊宏 喻光锋 | 2025-06-19 | Closed
8 | 604-59891 | Scratch | #VALUE! |  | 1.25% |  | The production assembly line consists of three processes: first assembly, magnetizing, and second assembly. The abnormality occurred during the magnetizing process, where burrs on the magnetizing board's acupuncture points caused scratches when removing the semi-finished products after magnetization. 此次生产组装线是有三道工序，一道组装——充磁——二道组装，异常发生在充磁工序，充磁治具板穴位有毛刺导致磁钢在充完磁后取下时被划伤。 | Repaired and remagnetized fixture, no scratches after deburring and milling. 返修充磁治具，铣去毛刺后无划伤产生。 | 桑涛 喻光锋 | 2025-06-18 | Closed
9 |  | Magnet misalignment | #VALUE! |  | 0.81% |  | "This anomaly occurred after magnetization, due to the influence of the Halbach array, the repulsive force between magnets increased. Additionally, the curing time of the 326 adhesive was too long, resulting in magnet detachment. 此异常出现在充磁之后，受海尔贝克阵列影响，磁钢之间排斥力增大，外加326胶水的固化时间过长，导致磁钢脱落" | "Technical personnel are continuously analyzing. 技术持续分析中。" | 桑涛 陈俊宏 喻光锋 | TBD | Cancel
10 |  | Foreign | #VALUE! |  | 0.6% |  | "Excessive dispensing of adhesive during production causes overflow and the formation of foreign. 生产过程中点胶过多导致胶水溢出形成异物。" | "Adjust the dispensing machine to reduce glue output fluctuation. 调试点胶机，减小出胶量波动。" | 桑涛 喻光锋 | 2025-06-25 | Closed

## PP Magnet MIL
APN | Issue | P1 |  |  | EVT |  |  | DVT |  |  | MP
|  | Qty Loss | Total Qty | Yield | Qty Loss | Total Qty | Yield | Qty Loss | Total Qty | Yield | Qty Loss | Total Qty | Yield
160-05757(1) | chips | 12 | 1200 | 1% | / | / | /
160-05757(1) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05757(1) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05761(2) | chips | 9 | 1200 | 0.75% | / | / | /
160-05761(2) | scratch | 4 | 1200 | 0.3333% | / | / | /
160-05761(2) | machine mark | 2 | 1200 | 0.1667% | / | / | /
160-05762(3) | chips | 12 | 1200 | 1% | / | / | /
160-05762(3) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05762(3) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05765(4) | chips | 15 | 1200 | 1.25% | / | / | /
160-05765(4) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05765(4) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05760(5) | chips | 10 | 1200 | 0.8333% | / | / | /
160-05760(5) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05760(5) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05758(6) | chips | 10 | 1200 | 0.8333% | / | / | /
160-05758(6) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05758(6) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05764(7) | chips | 11 | 1200 | 0.9167% | / | / | /
160-05764(7) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05764(7) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05759(8) | chips | 12 | 1200 | 1% | / | / | /
160-05759(8) | scratch | 8 | 1200 | 0.6667% | / | / | /
160-05759(8) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05763(9) | chips | 13 | 1200 | 1.083% | / | / | /
160-05763(9) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05763(9) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05549(10) | burr | 32 | 2400 | 1.333% | / | / | /
160-05549(10) | chips | 20 | 2400 | 0.8333% | / | / | /
160-05549(10) | bulge | 10 | 2400 | 0.4167% | / | / | /
160-05550(11) | burr | 33 | 2400 | 1.375% | / | / | /
160-05550(11) | chips | 15 | 2400 | 0.625% | / | / | /
160-05550(11) | bulge | 9 | 2400 | 0.375% | / | / | /
160-05551(12) | burr | 15 | 1200 | 1.25% | / | / | /
160-05551(12) | chips | 9 | 1200 | 0.75% | / | / | /
160-05551(12) | bulge | 5 | 1200 | 0.4167% | / | / | /
160-05552(13) | burr | 30 | 2400 | 1.25% | / | / | /
160-05552(13) | chips | 24 | 2400 | 1% | / | / | /
160-05552(13) | bulge | 8 | 2400 | 0.3333% | / | / | /
160-05553(14) | burr | 35 | 2400 | 1.458% | / | / | /
160-05553(14) | chips | 21 | 2400 | 0.875% | / | / | /
160-05553(14) | bulge | 11 | 2400 | 0.4583% | / | / | /
160-05554(15) | chips | 12 | 1200 | 1% | / | / | /
160-05554(15) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05554(15) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05555(16) | chips | 12 | 1200 | 1% | / | / | /
160-05555(16) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05555(16) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05556(17) | burr | 34 | 2400 | 1.417% | / | / | /
160-05556(17) | chips | 16 | 2400 | 0.6667% | / | / | /
160-05556(17) | bulge | 10 | 2400 | 0.4167% | / | / | /
160-05766(18) | burr | 15 | 1200 | 1.25% | / | / | /
160-05766(18) | chips | 9 | 1200 | 0.75% | / | / | /
160-05766(18) | bulge | 5 | 1200 | 0.4167% | / | / | /
160-05767(19) | burr | 15 | 1200 | 1.25% | / | / | /
160-05767(19) | chips | 7 | 1200 | 0.5833% | / | / | /
160-05767(19) | bulge | 5 | 1200 | 0.4167% | / | / | /
160-05746(20) | chips | 13 | 1200 | 1.083% | / | / | /
160-05746(20) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05746(20) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05741(21) | chips | 12 | 1200 | 1% | / | / | /
160-05741(21) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05741(21) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05747(22) | chips | 12 | 1200 | 1% | / | / | /
160-05747(22) | scratch | 5 | 1200 | 0.4167% | / | / | /
160-05747(22) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05740(23) | chips | 10 | 1200 | 0.8333% | / | / | /
160-05740(23) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05740(23) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05745(24) | chips | 7 | 1200 | 0.5833% | / | / | /
160-05745(24) | scratch | 4 | 1200 | 0.3333% | / | / | /
160-05745(24) | machine mark | 2 | 1200 | 0.1667% | / | / | /
160-05742(25) | chips | 11 | 1200 | 0.9167% | / | / | /
160-05742(25) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05742(25) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05737(26) | chips | 11 | 1200 | 0.9167% | / | / | /
160-05737(26) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05737(26) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05743(27) | chips | 13 | 1200 | 1.083% | / | / | /
160-05743(27) | scratch | 8 | 1200 | 0.6667% | / | / | /
160-05743(27) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05738(28) | chips | 10 | 1200 | 0.8333% | / | / | /
160-05738(28) | scratch | 5 | 1200 | 0.4167% | / | / | /
160-05738(28) | machine mark | 2 | 1200 | 0.1667% | / | / | /
160-05739(29) | chips | 36 | 4800 | 0.75% | / | / | /
160-05739(29) | scratch | 22 | 4800 | 0.4583% | / | / | /
160-05739(29) | machine mark | 11 | 4800 | 0.2292% | / | / | /
160-05570(30) | chips | 7 | 1200 | 0.5833% | / | / | /
160-05570(30) | scratch | 3 | 1200 | 0.25% | / | / | /
160-05570(30) | machine mark | 2 | 1200 | 0.1667% | / | / | /
160-05571(31) | burr | 17 | 1200 | 1.417% | / | / | /
160-05571(31) | chips | 14 | 1200 | 1.167% | / | / | /
160-05571(31) | bulge | 5 | 1200 | 0.4167% | / | / | /
160-05748(32) | burr | 13 | 1200 | 1.083% | / | / | /
160-05748(32) | chips | 8 | 1200 | 0.6667% | / | / | /
160-05748(32) | bulge | 4 | 1200 | 0.3333% | / | / | /
160-05744(33) | burr | 16 | 1200 | 1.333% | / | / | /
160-05744(33) | chips | 10 | 1200 | 0.8333% | / | / | /
160-05744(33) | bulge | 5 | 1200 | 0.4167% | / | / | /
160-05751(34) | chips | 48 | 4800 | 1% | / | / | /
160-05751(34) | scratch | 29 | 4800 | 0.6042% | / | / | /
160-05751(34) | machine mark | 15 | 4800 | 0.3125% | / | / | /
160-05577(35) | burr | 43 | 2400 | 1.792% | / | / | /
160-05577(35) | chips | 20 | 2400 | 0.8333% | / | / | /
160-05577(35) | bulge | 12 | 2400 | 0.5% | / | / | /
160-05578(36) | burr | 103 | 7200 | 1.431% | / | / | /
160-05578(36) | chips | 62 | 7200 | 0.8611% | / | / | /
160-05578(36) | bulge | 31 | 7200 | 0.4306% | / | / | /
160-05579(37) | burr | 24 | 2400 | 1% | / | / | /
160-05579(37) | chips | 19 | 2400 | 0.7917% | / | / | /
160-05579(37) | bulge | 7 | 2400 | 0.2917% | / | / | /
160-05580(38) | burr | 18 | 1200 | 1.5% | / | / | /
160-05580(38) | chips | 11 | 1200 | 0.9167% | / | / | /
160-05580(38) | bulge | 6 | 1200 | 0.5% | / | / | /
160-05583(39) | chips | 31 | 7200 | 0.4306% | / | / | /
160-05583(39) | scratch | 19 | 7200 | 0.2639% | / | / | /
160-05583(39) | machine mark | 10 | 7200 | 0.1389% | / | / | /
160-05584(40) | chips | 86 | 9600 | 0.8958% | / | / | /
160-05584(40) | scratch | 52 | 9600 | 0.5417% | / | / | /
160-05584(40) | machine mark | 26 | 9600 | 0.2708% | / | / | /
160-05585(41) | chips | 38 | 7200 | 0.5278% | / | / | /
160-05585(41) | scratch | 17 | 7200 | 0.2361% | / | / | /
160-05585(41) | machine mark | 7 | 7200 | 0.09722% | / | / | /
160-05586(42) | chips | 9 | 1200 | 0.75% | / | / | /
160-05586(42) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05586(42) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05587(43) | chips | 43 | 6000 | 0.7167% | / | / | /
160-05587(43) | scratch | 26 | 6000 | 0.4333% | / | / | /
160-05587(43) | machine mark | 13 | 6000 | 0.2167% | / | / | /
160-05589(44) | chips | 10 | 1200 | 0.8333% | / | / | /
160-05589(44) | scratch | 5 | 1200 | 0.4167% | / | / | /
160-05589(44) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05590(45) | chips | 13 | 2400 | 0.5417% | / | / | /
160-05590(45) | scratch | 8 | 2400 | 0.3333% | / | / | /
160-05590(45) | machine mark | 4 | 2400 | 0.1667% | / | / | /
160-05750(46) | chips | 11 | 1200 | 0.9167% | / | / | /
160-05750(46) | scratch | 7 | 1200 | 0.5833% | / | / | /
160-05750(46) | machine mark | 4 | 1200 | 0.3333% | / | / | /
160-05592(47) | chips | 7 | 1200 | 0.5833% | / | / | /
160-05592(47) | scratch | 3 | 1200 | 0.25% | / | / | /
160-05592(47) | machine mark | 2 | 1200 | 0.1667% | / | / | /
160-05593(48) | chips | 9 | 1200 | 0.75% | / | / | /
160-05593(48) | scratch | 6 | 1200 | 0.5% | / | / | /
160-05593(48) | machine mark | 3 | 1200 | 0.25% | / | / | /
160-05752(49) | chips | 24 | 2400 | 1% | / | / | /
160-05752(49) | scratch | 11 | 2400 | 0.4583% | / | / | /
160-05752(49) | machine mark | 5 | 2400 | 0.2083% | / | / | /
160-05557(51) | chips | 13 | 2400 | 0.5417% | / | / | /
160-05557(51) | scratch | 8 | 2400 | 0.3333% | / | / | /
160-05557(51) | machine mark | 4 | 2400 | 0.1667% | / | / | /
160-05755(52) | burr | 14 | 1200 | 1.167% | / | / | /
160-05755(52) | chips | 7 | 1200 | 0.5833% | / | / | /
160-05755(52) | bulge | 4 | 1200 | 0.3333% | / | / | /
160-05756(53) | burr | 15 | 1200 | 1.25% | / | / | /
160-05756(53) | chips | 12 | 1200 | 1% | / | / | /
160-05756(53) | bulge | 4 | 1200 | 0.3333% | / | / | /
160-05846(1) | chips | / | / | / | 25 | 3534 | 0.7074%
160-05846(1) | scratch | / | / | / | 20 | 3634 | 0.5504%
160-05846(1) | bulge | / | / | / | 7 | 3634 | 0.1926%
160-05847(2) | scratch | / | / | / | 19 | 3497 | 0.5433%
160-05847(2) | bulge | / | / | / | 9 | 3497 | 0.2574%
160-05847(2) | laser shift | / | / | / | 4 | 3497 | 0.1144%
160-05849(3) | bulge | / | / | / | 30 | 3680 | 0.8152%
160-05849(3) | scratch | / | / | / | 17 | 3680 | 0.462%
160-05849(3) | laser unclear | / | / | / | 10 | 3680 | 0.2717%
160-05851(4) | scratch | / | / | / | 34 | 3690 | 0.9214%
160-05851(4) | laser shift | / | / | / | 19 | 3690 | 0.5149%
160-05851(4) | bulge | / | / | / | 11 | 3690 | 0.2981%
160-05844(5) | bulge | / | / | / | 41 | 3603 | 1.138%
160-05844(5) | scratch | / | / | / | 19 | 3603 | 0.5273%
160-05844(5) | laser unclear | / | / | / | 7 | 3603 | 0.1943%
160-05852(6) | laser unclear | / | / | / | 30 | 3594 | 0.8347%
160-05852(6) | bulge | / | / | / | 17 | 3594 | 0.473%
160-05852(6) | scratch | / | / | / | 10 | 3594 | 0.2782%
160-05850(7) | chips | / | / | / | 17 | 3732 | 0.4555%
160-05850(7) | scratch | / | / | / | 9 | 3732 | 0.2412%
160-05850(7) | bulge | / | / | / | 4 | 3732 | 0.1072%
160-05848(8) | chips | / | / | / | 28 | 3546 | 0.7896%
160-05848(8) | scratch | / | / | / | 12 | 3546 | 0.3384%
160-05848(8) | bulge | / | / | / | 8 | 3546 | 0.2256%
160-05845(9) | chips | / | / | / | 16 | 3474 | 0.4606%
160-05845(9) | bulge | / | / | / | 9 | 3474 | 0.2591%
160-05845(9) | laser unclear | / | / | / | 4 | 3474 | 0.1151%
160-05549(10) | burr | / | / | / | 46 | 8672 | 0.5304%
160-05549(10) | bulge | / | / | / | 36 | 8672 | 0.4151%
160-05549(10) | chips | / | / | / | 13 | 8672 | 0.1499%
160-05550(11) | burr | / | / | / | 58 | 8656 | 0.6701%
160-05550(11) | chips | / | / | / | 36 | 8656 | 0.4159%
160-05550(11) | bulge | / | / | / | 14 | 8656 | 0.1617%
160-05551(12) | burr | / | / | / | 36 | 4559 | 0.7896%
160-05551(12) | chips | / | / | / | 15 | 4559 | 0.329%
160-05551(12) | bulge | / | / | / | 14 | 4559 | 0.3071%
160-05552(13) | bulge | / | / | / | 60 | 8748 | 0.6859%
160-05552(13) | burr | / | / | / | 31 | 8748 | 0.3544%
160-05552(13) | chips | / | / | / | 15 | 8748 | 0.1715%
160-05553(14) | bulge | / | / | / | 52 | 8502 | 0.6116%
160-05553(14) | burr | / | / | / | 28 | 8502 | 0.3293%
160-05553(14) | chips | / | / | / | 17 | 8502 | 0.2%
160-05554(15) | chips | / | / | / | 23 | 4324 | 0.5319%
160-05554(15) | bulge | / | / | / | 14 | 4324 | 0.3238%
160-05554(15) | scratch | / | / | / | 6 | 4324 | 0.1388%
160-05555(16) | scratch | / | / | / | 31 | 4566 | 0.6789%
160-05555(16) | chips | / | / | / | 21 | 4566 | 0.4599%
160-05555(16) | bulge | / | / | / | 6 | 4566 | 0.1314%
160-05556(17) | burr | / | / | / | 64 | 8616 | 0.7428%
160-05556(17) | chips | / | / | / | 31 | 8616 | 0.3598%
160-05556(17) | bulge | / | / | / | 22 | 8616 | 0.2553%
160-05842(18) | burr | / | / | / | 25 | 3742 | 0.6681%
160-05842(18) | bulge | / | / | / | 15 | 3742 | 0.4009%
160-05842(18) | chips | / | / | / | 9 | 3742 | 0.2405%
160-05843(19) | chips | / | / | / | 36 | 3629 | 0.992%
160-05843(19) | scratch | / | / | / | 24 | 3629 | 0.6613%
160-05843(19) | burr | / | / | / | 17 | 3629 | 0.4684%
160-05861(20) | chips | / | / | / | 15 | 3514 | 0.4269%
160-05861(20) | laser unclear | / | / | / | 9 | 3514 | 0.2561%
160-05861(20) | scratch | / | / | / | 4 | 3514 | 0.1138%
160-05857(21) | chips | / | / | / | 19 | 3582 | 0.5304%
160-05857(21) | laser shift | / | / | / | 10 | 3582 | 0.2792%
160-05857(21) | scratch | / | / | / | 7 | 3582 | 0.1954%
160-05858(22) | scratch | / | / | / | 31 | 3644 | 0.8507%
160-05858(22) | chips | / | / | / | 16 | 3644 | 0.4391%
160-05858(22) | bulge | / | / | / | 8 | 3644 | 0.2195%
160-05859(23) | chips | / | / | / | 26 | 3609 | 0.7204%
160-05859(23) | bulge | / | / | / | 19 | 3609 | 0.5265%
160-05859(23) | scratch | / | / | / | 10 | 3609 | 0.2771%
160-05860(24) | bulge | / | / | / | 29 | 3723 | 0.7789%
160-05860(24) | laser shift | / | / | / | 13 | 3723 | 0.3492%
160-05860(24) | chips | / | / | / | 9 | 3723 | 0.2417%
160-05855(25) | laser unclear | / | / | / | 24 | 3692 | 0.6501%
160-05855(25) | scratch | / | / | / | 8 | 3692 | 0.2167%
160-05855(25) | bulge | / | / | / | 7 | 3692 | 0.1896%
160-05856(26) | scratch | / | / | / | 30 | 3688 | 0.8134%
160-05856(26) | chips | / | / | / | 16 | 3688 | 0.4338%
160-05856(26) | laser unclear | / | / | / | 6 | 3688 | 0.1627%
160-05853(27) | laser unclear | / | / | / | 19 | 3738 | 0.5083%
160-05853(27) | chips | / | / | / | 13 | 3738 | 0.3478%
160-05853(27) | scratch | / | / | / | 4 | 3738 | 0.107%
160-05854(28) | laser shift | / | / | / | 17 | 3729 | 0.4559%
160-05854(28) | chips | / | / | / | 9 | 3729 | 0.2414%
160-05854(28) | bulge | / | / | / | 4 | 3729 | 0.1073%
160-05841(29) | chips | / | / | / | 282 | 27158 | 1.038%
160-05841(29) | scratch | / | / | / | 220 | 27158 | 0.8101%
160-05841(29) | bulge | / | / | / | 117 | 27158 | 0.4308%
160-05570(30) | chips | / | / | / | 26 | 4499 | 0.5779%
160-05570(30) | bulge | / | / | / | 16 | 4499 | 0.3556%
160-05570(30) | scratch | / | / | / | 7 | 4499 | 0.1556%
160-05571(31) | bulge | / | / | / | 24 | 4554 | 0.527%
160-05571(31) | burr | / | / | / | 16 | 4554 | 0.3513%
160-05571(31) | chips | / | / | / | 6 | 4554 | 0.1318%
160-05748(32) | bulge | / | / | / | 35 | 4512 | 0.7757%
160-05748(32) | burr | / | / | / | 23 | 4512 | 0.5098%
160-05748(32) | chips | / | / | / | 9 | 4512 | 0.1995%
160-05744(33) | burr | / | / | / | 41 | 4482 | 0.9148%
160-05744(33) | chips | / | / | / | 30 | 4482 | 0.6693%
160-05744(33) | bulge | / | / | / | 15 | 4482 | 0.3347%
160-06041(34) | bulge | / | / | / | 95 | 7089 | 1.34%
160-06041(34) | chips | / | / | / | 45 | 7089 | 0.6348%
160-06041(34) | burr | / | / | / | 10 | 7089 | 0.1411%
160-05578(35) | chips | / | / | / | 175 | 25422 | 0.6884%
160-05578(35) | bulge | / | / | / | 89 | 25422 | 0.3501%
160-05578(35) | burr | / | / | / | 556 | 25422 | 2.187%
160-05579(36) | burr | / | / | / | 73 | 8742 | 0.835%
160-05579(36) | chips | / | / | / | 35 | 8742 | 0.4004%
160-05579(36) | bulge | / | / | / | 13 | 8742 | 0.1487%
160-05580(37) | burr | / | / | / | 15 | 4505 | 0.333%
160-05580(37) | chips | / | / | / | 6 | 4505 | 0.1332%
160-05580(37) | bulge | / | / | / | 5 | 4505 | 0.111%
160-05583(38) | scratch | / | / | / | 219 | 25459 | 0.8602%
160-05583(38) | chips | / | / | / | 107 | 25459 | 0.4203%
160-05583(38) | bulge | / | / | / | 33 | 25459 | 0.1296%
160-05584(39) | chips | / | / | / | 58 | 33861 | 0.1713%
160-05584(39) | scratch | / | / | / | 37 | 33861 | 0.1093%
160-05584(39) | bulge | / | / | / | 27 | 33861 | 0.07974%
160-05585(40) | chips | / | / | / | 158 | 25418 | 0.6216%
160-05585(40) | scratch | / | / | / | 66 | 25418 | 0.2597%
160-05585(40) | bulge | / | / | / | 46 | 25418 | 0.181%
160-05586(41) | scratch | / | / | / | 45 | 4554 | 0.9881%
160-05586(41) | chips | / | / | / | 21 | 4554 | 0.4611%
160-05586(41) | bulge | / | / | / | 8 | 4554 | 0.1757%
160-05587(42) | scratch | / | / | / | 141 | 21320 | 0.6614%
160-05587(42) | chips | / | / | / | 75 | 21320 | 0.3518%
160-05587(42) | bulge | / | / | / | 55 | 21320 | 0.258%
160-05589(43) | chips | / | / | / | 25 | 4478 | 0.5583%
160-05589(43) | scratch | / | / | / | 10 | 4478 | 0.2233%
160-05589(43) | bulge | / | / | / | 8 | 4478 | 0.1787%
160-05590(44) | chips | / | / | / | 83 | 8694 | 0.9547%
160-05590(44) | bulge | / | / | / | 43 | 8694 | 0.4946%
160-05590(44) | scratch | / | / | / | 13 | 8694 | 0.1495%
160-05750(45) | bulge | / | / | / | 35 | 4432 | 0.7897%
160-05750(45) | chips | / | / | / | 20 | 4432 | 0.4513%
160-05750(45) | scratch | / | / | / | 12 | 4432 | 0.2708%
160-05592(46) | bulge | / | / | / | 28 | 4510 | 0.6208%
160-05592(46) | chips | / | / | / | 17 | 4510 | 0.3769%
160-05592(46) | scratch | / | / | / | 8 | 4510 | 0.1774%
160-05593(47) | chips | / | / | / | 24 | 4599 | 0.5219%
160-05593(47) | scratch | / | / | / | 16 | 4599 | 0.3479%
160-05593(47) | bulge | / | / | / | 9 | 4599 | 0.1957%
160-05752(48) | bulge | / | / | / | 44 | 8670 | 0.5075%
160-05752(48) | chips | / | / | / | 22 | 8670 | 0.2537%
160-05752(48) | scratch | / | / | / | 16 | 8670 | 0.1845%
160-05557(49) | scratch | / | / | / | 62 | 8668 | 0.7153%
160-05557(49) | bulge | / | / | / | 36 | 8668 | 0.4153%
160-05557(49) | chips | / | / | / | 10 | 8668 | 0.1154%
160-05755(50) | burr | / | / | / | 42 | 4589 | 0.9152%
160-05755(50) | bulge | / | / | / | 31 | 4589 | 0.6755%
160-05755(50) | chips | / | / | / | 12 | 4589 | 0.2615%
160-05756(51) | bulge | / | / | / | 37 | 4418 | 0.8375%
160-05756(51) | chips | / | / | / | 24 | 4418 | 0.5432%
160-05756(51) | burr | / | / | / | 11 | 4418 | 0.249%

## PP Magnet_MIL
Magnet Type: Piece Part
No | Issue Description | APN | Yield Loss By Build |  |  |  | Root Cause | Corrective Action | DRI | Due Date | Status
|  |  | P1 | P2 | EVT | MP
APN1
APN2
APN3

## Acoustic foam (hidden)
NO. | A P/N | Pic | Issue | Root cause | Improvement action | DRI | Date | ww | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK37 | WK38
[8 empty] | APN | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02 | 875-11250-02
[8 empty] | Yield | 94.32% | 94.57% | 94.48% | no input | no input | no input | no input | no input | no input | no input | no input
[8 empty] | Total Output | WK22: 11100; WK23: 6425; WK24: 9985
1 | 875-11250-02 |  | missing piece | Process-proteckive film peel force was lighter, lead the missing piece. | Add the peel force of process-proteck film from1~3g/in to 6~12g/in | Chentao | 2022-06-14 | Defect Qty | WK22: 330; WK23: 203
[8 empty] | % | 2.973% | 3.16% | 0% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
2 |  |  | Scarp residual | When discharging, the Scarp was too narrow,there is easy to broken, lead to Scrap residual on the product. | Add a layer of the protective film, to prevent the scarp broken. | Chentao | 2022-06-14 | Defect Qty | WK22: 300; WK23: 146
[8 empty] | % | WK22: 2.703%; WK23: 2.272%; WK24: 0%; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!; WK29: #DIV/0!
4 |  |  | Residual adhesive | The tooling blad have the residual adhesive , tranfer to the product | Add the cleaning freuency of the tooling from 4H/times to 2H/times. | Liuship | 2022-06-22 | Defect Qty | WK24: 335
[8 empty] | % | WK22: 0%; WK23: 0%; WK24: 3.355%; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!; WK29: #DIV/0!
5 |  |  | Foam edge step | Tooling A and Tooling B had the matched issue. | adjuest the Tooling B. | Chentao | 2022-06-25 | Defect Qty | WK24: 216
[8 empty] | % | WK22: 0%; WK23: 0%; WK24: 2.163%; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!; WK29: #DIV/0!

## Foam (hidden)
NO. | A P/N | Pic | Issue | Root cause | Improvement action | DRI | Date | ww | EVT | WK22 | WK23 | WK24 | WK25 | WK26 | WK27 | WK28 | WK29 | WK30 | WK31 | WK32 | WK33 | WK34 | WK35 | WK36
[8 empty] | APN | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03 | 870-15765-03
[8 empty] | Yield | 93.15% | no input | no input | no input | no input | no input | no input | no input | no input | no input | no input | no input
[8 empty] | Total Output | 8948
1 | 870-15765-03 |  | Press mark | The copper foil has a memory material,as the corners is smaller, the cooper was pressed when stamping, lead to the wrinkle issue. | Repair the tooling, to reduce the press mark . | xuxiaodong | 2022-06-08 | Defect Qty | 613
[8 empty] | % | 6.851% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
2 | [7 empty] | Defect Qty
[8 empty] | % | 0% | WK22: #DIV/0!; WK23: #DIV/0!; WK24: #DIV/0!; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!
3 | [7 empty] | Defect Qty
[8 empty] | % | 0% | WK22: #DIV/0!; WK23: #DIV/0!; WK24: #DIV/0!; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!
4 | [7 empty] | Defect Qty
[8 empty] | % | 0% | WK22: #DIV/0!; WK23: #DIV/0!; WK24: #DIV/0!; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!
5 | [7 empty] | Defect Qty
[8 empty] | % | 0% | WK22: #DIV/0!; WK23: #DIV/0!; WK24: #DIV/0!; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!
6 | [7 empty] | Defect Qty
[8 empty] | % | 0% | WK22: #DIV/0!; WK23: #DIV/0!; WK24: #DIV/0!; WK25: #DIV/0!; WK26: #DIV/0!; WK27: #DIV/0!; WK28: #DIV/0!